## Tabelle1
Risk | Description | Prob. Of Occurrence | Damage | Mitigation Strategy | Person in Charge | Risk Factor
Change of API Structure | Data source changes its API structure -> data retrival no longer works | 5% | 20% | use external libaries -> update automatically | Jannik | 1%
Change of API Costs | API changes cost structure -> too expencive | 10% | 50% | integrate multiple social media platforms | Christian | 5%
Heroku not accessable | Ist not possible to access the date from heroku any more | 5% | 100% | Make backups | Nicki | 5%
Project not finished till deadline | Not all usecases realized due to bad/missing planning | 25% | 30% | organize/divide time well | Alina | 7.5%
Transfer of knowledge | All team members needs to be on the same theoretical Stage | 70% | 70% | Create tutorials, don't hesitate to ask -> better communication | Nicki | 49%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%